## Sheet1
NopCommerce Manual Testing Project
Defect Report
Generated Date: January 08, 2026 ¦ Author: QA Automation Lead ¦ Environment: demo.nopcommerce.com
Description: Log of bugs and issues found during execution.
Defect ID | Test Case ID | Module | Severity | Priority | Description | Status | Reported Date
BUG_001 | TC_12 | Wishlist | Medium | P2 | Wishlist count not updating immediately after adding item | Open | 2023-10-25
BUG_002 | TC_25 | Responsive | High | P1 | Hamburger menu not opening on iPhone SE Resolution | Open | 2023-10-25
BUG_003 | TC_40 | Checkout | Critical | P1 | Credit Card payment spinner hangs on slow network | Fixed | 2023-10-26
BUG_004 | TC_45 | Search | Low | P3 | Search suggestion case sensitivity mismatch | Won't Fix | 2023-10-27